## Classification
Internal

## Summary
Functional/System Admin Estimate Summary
Internal Document not to be shared with the customer
Note: Task breakdown can be elaborated further based on the CR you are estimating the template is a guideline of things to consider when preparing an estimate
QMS Code: FTD_MS_EST 0475
Customer: | Gold Coin
Ticket Reference/Modification Name:
Estimate Summary | Person Hours
Total Task Estimate | 16
Total Billable Estimate | 16
Document Control
Version | 1.2
Release date
Functional Estimate prepared by | Jaliya Hewage
Technical Estimate prepared by | Enter consultant name
System Administrator Estimate prepared by | Enter consultant name
Reviewed By
Functional Review | Mohammed Safwan
Technical Review | Enter consultant name
System Administrator Review | Enter consultant name

## Task Breakdown
Task/Phase | Responsible | Deliverable | Functional Consultant Finance (Hrs) | Functional Consultant Non-Finance (Hrs) | Solution Architect (Hrs) | System Administrator (Hrs) | Technical (Hrs) | Quality Assurance (Hrs) | Project Management (Hrs) |  | Comments | Guideline
Discovery | [6 empty] | Not Applicable
Business Requirement Study | FC |  | 2 | [6 empty] | (Billable)
Documentation of Requirements | FC | Business Requirement Specification for M3 Add-on | 4 | [6 empty] | (Billable)
Elaborate
Conceptual Solution design | FC |  | 3 | [6 empty] | (Billable) |  | Time spent to design, present and discuss the solution with the customer
Functional Specification Update/Create | FC | Functional Specification | [7 empty] | (Billable)
Spec walkthrough with Customer | FC | [8 empty] | (Billable) |  | This is optional if the customer requests for a walk through
Spec walkthrough with Tech Team | FC |  | 1 | [6 empty] | (Billable) |  | This is to walk the technical team through the spec and requirement once design is confirmed
M3 Configuration Activities (Non-Production) | FC/SA | [8 empty] | (Billable) |  | Please consider the number of non-PRD environments
Data conversion/ Cutover | FC | [8 empty] | (Billable) |  | Are there any Bulk data uploads that need to be done
Testing & Test Case Documentation | FC | Test Case Document | 4 | [6 empty] | (Billable) |  | Use 'Test Scenario' Tab to list down what will be covered at a high level
User Manuals/Documentation | FC | Quick Reference Guide | [7 empty] | (Billable) |  | Upon request from the customer
Key User training | FC | [8 empty] | (Billable) |  | Upon request from the customer
UAT support | FC | [8 empty] | (Billable) |  | Upon request from the customer
Contingency buffer | FCL |  | 1 | [6 empty] | (Billable)
Transition
M3 Configuration Activities (Production) | FC/SA | [8 empty] | (Billable)
Data conversion/ Cutover | FC/SA | [8 empty] | (Billable) |  | Are there any Bulk data uploads that need to be done
Configuration/ Blueprint document update | FC | [8 empty] | (Billable) |  | If required only
Production Deployment Forms/Requests | FC | [8 empty] | (Billable) |  | Change request forms. If internal CAB then Non-Billable
Post verification testing | FC |  | 1 | [6 empty] | (Billable) |  | Verification after deployment if it is working as expected. If this can only be done by the user this will not be billable
Support Handover | FC | [8 empty] | (Billable)
Hypercare | FC | [8 empty] | (Billable)
Technical Estimate
Requirement Gathering and Design Discussion | TC | [8 empty] | (Non-Billable)
Development task Break down | TC | [8 empty] | (Billable)
Task 1 | TC | [8 empty] | (Billable)
Task 2 | TC | [8 empty] | (Billable)
Testing | TC | [8 empty] | (Billable)
Documents | TC | [8 empty] | (Billable)
Release notes | TC | [8 empty] | (Billable)
DES020 | TC | [8 empty] | (Billable)
Deployment | TC | [8 empty] | (Billable)
Hypercare | TC | [8 empty] | (Billable)
Contingency buffer | TCL | [8 empty] | (Billable)
Quality Assurance
QA test case preparation | QA | QA Test Plan/ Test case document | [7 empty] | (Billable)
QA testing | QA | Test Results | [7 empty] | (Billable)
Project Management
Project Management/ Service Management | SM | [8 empty] | (Billable)
Contingency buffer | SM | [8 empty] | (Billable)
Total Effort per Resource |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0
Total Billable Effort |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0
Rate per hour |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billable Amount per Resource |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total CR cost |  | 0

## Test Scenarios
Scenarios to be tested/considered

## Scope
Scope
Out of Scope
Deliverables
Updated Functional/Technical spec
Testcase document

## Assumptions
Assumptions Functional
Assumptions Technical
Assumptions System Administrator

## Template Version Update
Version Number | Update
1 | Initial Template
1.1 | Template version Tab renamed
1.2 | Task Breakdown : Spec walkthrough with Tech Team under the 'Elaborate' section was made billable and the formula in the 'Summary' tab, the formula's for Total Task Estimate and Total Billable Estimate were revised.